## Sheet1
THESIS PROJECT PLAN | 2018-06-25 |  |  |  |  | 2018-07-02 |  |  |  |  | 2018-07-09 |  |  |  |  | 2018-07-16 |  |  |  |  | 2018-07-23 | [6 empty] | 2018-07-30 | [6 empty] | 2018-08-06 | [6 empty] | 2018-08-13 |  |  |  |  | 2018-08-20 |  |  |  |  | 2018-08-27 |  |  |  |  | 2018-09-03 |  |  |  |  | 2018-09-10 |  |  |  |  | 2018-09-17 |  |  |  |  | 2018-09-24 |  |  |  |  | 2018-10-01 |  |  |  |  | 2018-10-08 |  |  |  |  | 2018-10-15 |  |  |  |  | 2018-10-22
| M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | 30p wide
Planning + revision: of project + previous work | [96 empty] | 60p high
Educate: watch fast.ai part 2, read papers and blogs
Set up pi: everything got mangled -> reinstall
Hardware test: compile NN into graph, put on NCS
Set up minibeast: install python, tensorflow, etc
Data: collect + label data of humans, preprocessing
Create NN: recognise an obj + find it in the frame
Compile a NN: switch to tf, finetune model, compile
Test the NCS: stick + NN + camera all works live
Camera gimbal: compare options, order
Camera gimbal 2: fetch, print frame, assemble, test
Extended Kalman Filter: understand + implement
Work on control: make it track pan + tilt
Integration time: put everything together, test
Convert to cheetah tracker: data, train
Work on "extras": eg put on quad, etc
Write up thesis: lit. review, make backups, LaTeX
Poster + presentation: sleep --> prepare

## Sheet1 (old)
THESIS PROJECT PLAN | 2018-06-25 |  |  |  |  | 2018-07-02 |  |  |  |  | 2018-07-09 |  |  |  |  | 2018-07-16 |  |  |  |  | 2018-07-23 | [6 empty] | 2018-07-30 | [6 empty] | 2018-08-06 | [6 empty] | 2018-08-13 |  |  |  |  | 2018-08-20 |  |  |  |  | 2018-08-27 |  |  |  |  | 2018-09-03 |  |  |  |  | 2018-09-10 |  |  |  |  | 2018-09-17 |  |  |  |  | 2018-09-24 |  |  |  |  | 2018-10-01 |  |  |  |  | 2018-10-08 |  |  |  |  | 2018-10-15 |  |  |  |  | 2018-10-22
| M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | 30p wide
Planning + revision: of project + previous work | [96 empty] | 60p high
Educate: watch fast.ai part 2, read papers and blogs
Set up pi: everything got mangled -> reinstall
Hardware test: compile NN into graph, put on NCS
Set up minibeast: install python, tensorflow, etc
Data: collect + label data of humans, preprocessing
Create NN: recognise an obj + find it in the frame
Compile a NN: switch to tf, finetune model, compile
Test the NCS: stick + NN + camera all works live
Camera gimbal: design, 3D print, put together
Extended Kalman Filter: understand + implement
Work on control: make it track pan + tilt
Buffer: just in case things take long
Convert to cheetah tracker: data, train
Work on "extras": eg put on quad, etc
Write up thesis: lit. review, make backups, LaTeX
Poster + presentation: sleep --> prepare