## Sheet1
THESIS PROJECT PLAN | 2018-06-25 |  |  |  |  | 2018-07-02 |  |  |  |  | 2018-07-09 |  |  |  |  | 2018-07-16 |  |  |  |  | 2018-07-23 |  |  |  |  | 2018-07-30 |  |  |  |  | 2018-08-06 |  |  |  |  | 2018-08-13 |  |  |  |  | 2018-08-20 |  |  |  |  | 2018-08-27 |  |  |  |  | 2018-09-03 |  |  |  |  | 2018-09-10 |  |  |  |  | 2018-09-17 |  |  |  |  | 2018-09-24 |  |  |  |  | 2018-10-01 |  |  |  |  | 2018-10-08 |  |  |  |  | 2018-10-15 |  |  |  |  | 2018-10-16
| M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | 30p wide
Planning + revision: of project + previous work | [90 empty] | 60p high
Educate: watch fast.ai part 2, read papers and blogs
Set up pi: everything got mangled -> reinstall
Hardware test: put NN onto NCS, test entire system
Data: collect + label photos + videos of dogs
Rig setup: set up the minibeast for NN training
Create NN: recognise dogs + draw a box around em
Camera gimbal: design + 3D print
Basic tracking algorithm: proportional (+ integrate?)
Kalman filter: understand + implement | holding off on any planning from this point on until I have a better
Improve control algorithm: make it track pan + tilt | idea of how busy I'll be during the semester/when tests + projects
Convert to cheetah tracker: collect + label new data | are due these are just preliminary estimates to get an idea of how | [39 empty] | https://storage.googleapis.com/openimages/web/download.html ???
Convert to cheetah tracker 2: tweak NN architecture | much time I'll have for things (eg one block is about 8 hours of
Write up thesis: do it in LaTeX | work now, but will be less during 3rd quarter and more in 4th)